19-AMRITSAR SOUTH — DETAILED 169-BOOTH MASTERPLAN
Booth-level field operations strategy based on 2022 Assembly vs 2024 Parliamentary Dataset (Amritsar PC)

## Purpose & Operational Framework

This document provides actionable field directives for all 169 polling stations of 19-Amritsar South. Every booth is assigned a concrete operational action sequence focused on urban cadre mobilization, merchant/trader engagement, ward civic grievance redressal, voter turnout revival, and repeat round visits.

## 90-Day Booth Engagement Cycle

• Days 1–30: Assign booth coordinators, assemble local mohalla committees, attach historical polling telemetry, and map geographic urban clusters.
• Days 31–45: Round 1 field visits — systematic community listening, record civic grievances (sanitation, water, roads, electricity), and verify voter list changes.
• Days 46–60: Follow-up — submit recorded civic grievances to municipal corporation and state departments, track progress systematically.
• Days 61–75: Round 2 field visits — return to booth, report progress on issues, engage local trader associations, and consolidate neighborhood leadership.
• Days 76–85: Remedial interventions — resolve inactive booth committees and address unaddressed local complaints in vulnerable wards.
• Days 86–90: Audit & Readiness — complete coverage verification, finalize voter mobilization rosters for 2027.

## Detailed Booth-by-Booth Plan (All 169 Booths)

| Booth | Locality / Polling Station | 2022 Winner | 2022 AAP | 2024 Winner | 2024 AAP | AAP Swing | Turnout Δ | Detailed Status | Detailed Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Booth 1 - Amritsar South | AAP | 53.76% | BJP | 29.35% | -24.4 pts | -18.7% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-24.4 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 2 | Booth 2 - Amritsar South | AAP | 45.86% | INC | 30.08% | -15.8 pts | -21.7% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-15.8 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 3 | Booth 3 - Amritsar South | AAP | 44.94% | BJP | 16.9% | -28.0 pts | -16.5% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-28.0 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 4 | Booth 4 - Amritsar South | AAP | 41.78% | BJP | 22.87% | -18.9 pts | -15.7% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-18.9 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 5 | Booth 5 - Amritsar South | AAP | 60.85% | BJP | 21.06% | -39.8 pts | -25.5% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-39.8 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 6 | Booth 6 - Amritsar South | AAP | 52.14% | BJP | 19.33% | -32.8 pts | -18.4% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-32.8 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 7 | Booth 7 - Amritsar South | AAP | 44.03% | BJP | 30.44% | -13.6 pts | -22.5% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-13.6 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 8 | Bhagtanwala Gali No. 4, Nagar Nigam Amritsar, Ward No. 49 + Bazar Munshian Wala, Nagar Nigam Amritsar, Ward No. 49 + Gali Mansood Choudhary, Nagar Nigam Amritsar, Ward No. 49 + Bazar Ghumiyaran Wala, Nagar Nigam Amritsar, Ward No. 49 + Gali Munshian Wali, Nagar Nigam Amritsar, Ward No. 49 + Katra Karam Singh, Nagar Nigam Amritsar, Ward No. 49 | AAP | 48.82% | BJP | 20.61% | -28.2 pts | -18.7% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-28.2 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 9 | Gali Hatam Bhai Andrun Gate Hakima, Nagar Nigam Amritsar, Ward No. 54 | AAP | 42.27% | BJP | 20.0% | -22.3 pts | -15.4% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-22.3 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 10 | Gali Khoiyan No. 1, Nagar Nigam Amritsar, Ward No. 54 + Gali Khoiyan No. 2, Nagar Nigam Amritsar, Ward No. 54 + Gali Hatam Bhai Baharla Pasa, Nagar Nigam Amritsar, Ward No. 54 + Gate Khazana Saja Pasa, Nagar Nigam Amritsar, Ward No. 54 + Circular Road Khazana Gate, Nagar Nigam Amritsar, Ward No. 54 | AAP | 44.22% | BJP | 21.88% | -22.3 pts | -29.0% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-22.3 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 11 | Booth 11 - Amritsar South | AAP | 53.25% | BJP | 17.65% | -35.6 pts | -17.1% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-35.6 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 12 | Booth 12 - Amritsar South | AAP | 47.8% | BJP | 21.79% | -26.0 pts | -16.1% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-26.0 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 13 | Booth 13 - Amritsar South | AAP | 53.47% | BJP | 16.91% | -36.6 pts | -41.0% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-36.6 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 14 | Booth 14 - Amritsar South | AAP | 46.91% | BJP | 16.67% | -30.2 pts | -24.8% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-30.2 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 15 | Booth 15 - Amritsar South | AAP | 42.1% | INC | 11.8% | -30.3 pts | -16.4% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-30.3 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 16 | Booth 16 - Amritsar South | SAD | 23.99% | INC | 9.56% | -14.4 pts | -30.5% | Opponent Transition: Won by SAD in 2022 and shifted to INC in 2024. Volatile urban battleground. | 1. Analyze underlying voter dissatisfaction shifting between opponents. 2. Project AAP as stable local governance choice. 3. Mobilize pro-AAP ward committee. |
| 17 | Abadi Radha Krishan Colony, Nagar Nigam Amritsar, Ward No. 50 + Abadi Quarters, Mulle Chak, Nagar Nigam Amritsar, Ward No. 50 | INC | 31.3% | INC | 26.42% | -4.9 pts | -14.4% | Opponent Stronghold: Retained by INC in both elections. Strategic long-term penetration zone. | 1. Identify neutral voter clusters & youth groups. 2. Highlight Punjab state guarantees & civic development work. 3. Continuous outreach to chip away at INC base. |
| 18 | Abadi Quarter, Mulle Chowk, Nagar Nigam Amritsar, Ward No. 50 | INC | 31.93% | INC | 12.76% | -19.2 pts | -12.3% | Opponent Stronghold: Retained by INC in both elections. Strategic long-term penetration zone. | 1. Identify neutral voter clusters & youth groups. 2. Highlight Punjab state guarantees & civic development work. 3. Continuous outreach to chip away at INC base. |
| 19 | Gali Chhiura Wali, Nagar Nigam Amritsar Ward No. 48 + Gali Devi Wali, (Jora Pipal) Nagar Nigam Amritsar, Ward No. 48 + Gali Nalke Wali, Nagar Nigam Amritsar, Ward No. 48 + Gali Pehalwana, Nagar Nigam Amritsar, Ward No. 48 + Gali Diwan Singh, Nagar Nigam Amritsar, Ward No. 48 + Gali Chela Ram, Nagar Nigam Amritsar, Ward No. 48 | AAP | 53.81% | BJP | 14.77% | -39.0 pts | -16.1% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-39.0 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 20 | Bazar Bhagtan Wala, Nagar Nigam Amritsar, Ward No. 48 + Gali Shahdin, Nagar Nigam Amritsar, Ward No. 48 + Bazar Gujran Wala, Nagar Nigam Amritsar, Ward No. 48 + Gali Masit Wali, Nagar Nigam Amritsar, Ward No. 48 + Bazar Gujran Chowk Chabutra, Nagar Nigam Amritsar, Ward No. 48 + Kucha Hari Singh, Nagar Nigam Amritsar, Ward No. 48 + Kucha Raiyan Wala, Nagar Nigam Amritsar, Ward No. 48 + Gali Shahdin, Nagar Nigam Amritsar Ward No. 48 + Gali Nati Baksh, Nagar Nigam Amritsar, Ward No. 48 | AAP | 48.1% | BJP | 16.39% | -31.7 pts | -27.9% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-31.7 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 21 | Kucha Gujran Wala, Nagar Nigam Amritsar, Ward No. 48 + Gali Guru Nanak Wali, Nagar Nigam, Amritsar, Ward No. 48 + Kucha Tahil Singh Circular Road Nagar Nigam Amritsar Ward No. 48 + Gali Sedhiyan, Nagar Nigam Amritsar, Ward No. 46 + Gali Moole Wali, Nagar Nigam Amritsar, Ward No. 46 | AAP | 51.48% | BJP | 24.95% | -26.5 pts | -14.6% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-26.5 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 22 | Gali Pehalwana Wali Bazar Bhagtan Wala, Nagar Nigam Amritsar, Ward No. 48 + Gali Tind Shah, Nagar Nigam Amritsar, Ward No. 48 + Mohalla Balmiki, Nagar Nigam Amritsar, Ward No. 48 + Mandir Wali Gali, Nagar Nigam Amritsar Ward No. 48 + Gali Dharek Wali, Nagar Nigam Amritsar Ward No. 48 | AAP | 46.52% | INC | 12.41% | -34.1 pts | -30.6% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-34.1 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 23 | Guru Teg Bahadur Avenue, Nagar Nigam Amritsar, Ward No. 46 + Bazaar Ghumiaran, Nagar Nigam Amritsar, Ward No. 48 + Gali Guru Nanak, Nagar Nigam Amritsar, Ward No. 48 + Gali Krishna, Nagar Nigam Amritsar, Ward No. 48 + Gali Mistra Nagar Nigam Amritsar, Ward No. 48 + Gali Jawala Wali, Nagar Nigam Amritsar, Ward No. 48 + Gali Chappar Wali, Nagar Nigam Amritsar, Ward No. 48 + Bazaar Ghumiaran Wala Near Shivala Behar Wala Chowk, Nagar Nigam Amritsar, Ward No. 48 | AAP | 58.74% | BJP | 30.59% | -28.1 pts | -17.7% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-28.1 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 24 | Kucha Rahimshu Khila, Nagar Nigam Amritsar, Ward No. 48 + Androon Gilwali Gate, Nagar Nigam Amritsar, Ward No. 48 + Bazaar Jattan Wala, Nagar Nigam Amritsar, Ward No. 48 + Gali Jameetan Kamboj, Nagar Nigam Amritsar, Ward No. 48 + Gali Aave Wali, Nagar Nigam Amritsar, Ward No. 48 | AAP | 62.98% | AAP | 34.14% | -28.8 pts | -20.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.14% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.14% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 25 | Gali Aave Wali, Androon Gate Bhagtanwala, Nagar Nigam Amritsar Ward No. 48 + Gali Megha Katra Garbha Singh, Nagar Nigam Amritsar. Ward No. 48, Amritsar. + Gali Aave Wali Devi, Androon Gate Bhagtanwala, Nagar Nigam Amritsar Ward No. 48 + Gali Rahimuj Bazar Gujra, Nagar Nigam Amritsar. Ward No. 48, Amritsar. + Bazar Gujra Katra Garbha Singh, Nagar Nigam Amritsar Ward No. 48, Amritsar. | AAP | 47.0% | BJP | 17.51% | -29.5 pts | -12.7% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-29.5 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 26 | Gali Taliyan Wali, Nagar Nigam Amritsar Ward No. 49 + Bazaar Jora Pippal, Nagar Nigam Amritsar Ward No. 48 + Gali Kamboj Wali, Nagar Nigam Amritsar Ward No. 48 + Bazaar Khooh Berian, Nagar Nigam Amritsar Ward No. 48 + Gali Aadivasian, Nagar Nigam Amritsar Ward No. 48 + Ram Gali, Jora Pippal, Nagar Nigam Amritsar Ward No. 48 + New Dashmesh Avenue Amritsar Ward No. 50 | AAP | 60.06% | BJP | 23.93% | -36.1 pts | -13.2% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-36.1 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 27 | Gali Veerowali, Nagar Nigam, Amritsar, Ward No. 49 + Gali Mela Singh, Nagar Nigam Amritsar, Ward No. 49 + Gali Dasodha Wali, Nagar Nigam Amritsar, Ward No. 49 + Hak Malviyan, Nagar Nigam Amritsar, Ward No. 48 + Bazaar Joda Pipal, Nagar Nigam Amritsar, Ward No. 48 + Gali Deva Singh, Nagar Nigam Amritsar, Ward No. 48 + Kucha Shaheed Pehalwan, Nagar Nigam Amritsar, Ward No. 48 + Kucha Dayal Singh, Nagar Nigam Amritsar, Ward No. 49 + Kanak Mandi, Nagar Nigam Amritsar, Ward No. 49 + Lakkar Mandi, Nagar Nigam Amritsar, Ward No. 49 + Chah Basti Ram, Nagar Nigam Amritsar, Ward No. 49 + Chitpurni Chowk, Nagar Nigam Amritsar, Ward No. 49 + Gali Tambaku Kuta, Nagar Nigam Amritsar, Ward No. 49 | AAP | 46.46% | BJP | 17.56% | -28.9 pts | -19.3% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-28.9 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 28 | Gali Veere Wali, Nagar Nigam Amritsar, Ward No. 49 + Gali Ichha Ram, Nagar Nigam Amritsar, Ward No. 49 + Shiv Gali, Nagar Nigam Amritsar, Ward No. 49 + Swank Mandi, Nagar Nigam Amritsar, Ward No. 49 | AAP | 51.05% | BJP | 10.64% | -40.4 pts | -23.1% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-40.4 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 29 | Bazaar Chhatrian, Nagar Nigam Amritsar, Ward No. 49 + Namak Mandi, Nagar Nigam Amritsar, Ward No. 49 + Gali Jandi Wali, Nagar Nigam Amritsar, Ward No. 49 + Kandhariyan Gali, Nagar Nigam Amritsar, Ward No. 49 | AAP | 44.15% | BJP | 11.84% | -32.3 pts | -23.8% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-32.3 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 30 | Gali Talian Wali, Nagar Nigam Amritsar, Ward No. 49 + Krishna Gali, Nagar Nigam Amritsar, Ward No. 49 | AAP | 50.37% | BJP | 24.61% | -25.8 pts | -14.2% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-25.8 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 31 | Chowk Bazar Lachhmansar, Nagar Nigam Amritsar, Ward No. 46 + Gali Gujjran Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Hansli Wali Kucha Harnam Das, Nagar Nigam Amritsar, Ward No. 46 + Kucha Deen (Neel Wali Gali), Nagar Nigam Amritsar, Ward No. 46 + Kucha Maape Shah Gali Hansli, Nagar Nigam Amritsar, Ward No. 46 + Kucha Deen Ghumiar, Nagar Nigam Amritsar, Ward No. 46 + Kucha Roadways Gali Hansli Wali, Nagar Nigam Amritsar, Ward No. 46 + Bazar Baba Sahib, Nagar Nigam Amritsar, Ward No. 46 + Gali Hansli Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Budha Singh, Nagar Nigam Amritsar, Ward No. 46 | AAP | 56.58% | BJP | 26.57% | -30.0 pts | -5.9% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-30.0 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 32 | Gali Suniarian, Nagar Nigam Amritsar, Ward No. 49 + Gali Beri Wali Katra Mit Singh, Nagar Nigam Amritsar, Ward No. 49 + Katra Dal Singh Bucha Kalian, Nagar Nigam Amritsar, Ward No. 49 + Meti Bazar Katra Mit Singh, Nagar Nigam Amritsar, Ward No. 49 + Katra Dal Singh Bucha Putap Singh, Nagar Nigam Amritsar, Ward No. 49 + Gali Makhaiyan Meti Bazar Katra Mit Singh, Nagar Nigam Amritsar, Ward No. 49 + Bazar Katra Mit Singh Bucha Balwant Singh, Nagar Nigam Amritsar, Ward No. 49 + Katra Mit Singh Pethe Wala Bazar, Nagar Nigam Amritsar, Ward No. 49 + Bazar Pethe Wala Katra Mit Singh, Nagar Nigam Amritsar, Ward No. 49 + Gali Ruda Mal Bhatia Meti Bazar, Nagar Nigam Amritsar, Ward No. 49 + Bazar Katra Mit Singh Gali Tara Chand, Nagar Nigam Amritsar, Ward No. 49 + Gali Bura Attar Meti Bazar, Nagar Nigam Amritsar, Ward No. 49 + Katra Mit Singh Gali Charan Singh, Nagar Nigam Amritsar, Ward No. 49 + Gali Sukha Thanedar Meti Bazar, Nagar Nigam Amritsar, Ward No. 49 + Gali Nikka Meti Bazar, Nagar Nigam Amritsar, Ward No. 49 | AAP | 57.14% | BJP | 25.61% | -31.5 pts | -21.8% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-31.5 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 33 | Gali Gujjran Wali, Nagar Nigam Amritsar Ward No. 46 + Gali Sangal Wali Nagar Nigam Amritsar, Ward No. 46 + Baba Sahib Chowk Gali Gujjran, Nagar Nigam Amritsar, Ward No. 46 + Gali Gujjran (Gali Jiwan Singh), Nagar Nigam Amritsar Ward No. 46 + Lakkad Mandi Dhab Basti Ram, Nagar Nigam Amritsar, Ward No. 46 + Kucha Dharname Shah, Nagar Nigam Amritsar, Ward No. 46 + Gali Bagh Wali (Kaka Singh), Nagar Nigam Amritsar, Ward No. 46 + Ram Vehra, Nagar Nigam Amritsar Ward No. 46 | AAP | 59.72% | AAP | 34.76% | -25.0 pts | -12.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.76% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.76% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 34 | Chawal Mandi Nagar Nigam Amritsar Ward No. 49 + Bazar Chatti Khuhi, Nagar Nigam Amritsar Ward No. 49 + Gali Mana Wali, Nagar Nigam Amritsar Ward No. 49 + Kucha Hari Ram Bazar Chatti Khuhi, Nagar Nigam Amritsar, Ward No. 49 + Bazar Chatti Khuhi Kucha Hari Dhobian, Nagar Nigam Amritsar, Ward No. 49 + Gali Khooh Wali Katra Dal Singh, Gali Arak Wali, Nagar Nigam Amritsar Ward No. 49 + Katra Dal Singh Arak Wali Gali Nagpal, Nagar Nigam Amritsar, Ward No. 49 + Gali Nagpal, Nagar Nigam Amritsar Ward No. 49 + Gali Arak Wali, Nagar Nigam Amritsar Ward No. 49 + Atta Mandi Chowk Chatti Khuhi Vehra Akalian, Nagar Nigam Amritsar, Ward No. 49 + Gali Chaudhrian Atta Mandi, Nagar Nigam Amritsar Ward No. 49 + Gali Dindi Mall, Nagar Nigam Amritsar Ward No. 49 + Gali Hansli, Nagar Nigam Amritsar Ward No. 49 + Gali Atta Mandi Dera Baba Sham Singh, Nagar Nigam Amritsar Ward No. 49 | AAP | 57.59% | BJP | 29.05% | -28.5 pts | -17.1% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-28.5 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 35 | Guru Ramdas Nagar Gali No. 1 Bhagtanwala Nagar Nigam Amritsar Ward No. 50 + S.D. School Amritsar, Nagar Nigam Amritsar Ward No. 50 + Thatheri Mohalla Bhagtanwala, Nagar Nigam Amritsar Ward No. 50 | SAD | 27.63% | INC | 24.77% | -2.9 pts | -11.6% | Opponent Transition: Won by SAD in 2022 and shifted to INC in 2024. Volatile urban battleground. | 1. Analyze underlying voter dissatisfaction shifting between opponents. 2. Project AAP as stable local governance choice. 3. Mobilize pro-AAP ward committee. |
| 36 | Anusuchit Jati Colony, Bhagtanwala Nagar Nigam Amritsar Ward No. 50 + Gurudware Wali Gali Main Road, Nagar Nigam Amritsar Ward No. 50 + Mohan Flour Mills, Nagar Nigam Amritsar Ward No. 50 + Guru Nanak Chips, Nagar Nigam Amritsar Ward No. 50 + Anusuchit Jati Colony, Main Gali, Nagar Nigam Amritsar Ward No. 50 + Balmik Mandir Bhagtanwala, Nagar Nigam Amritsar Ward No. 50 | INC | 28.44% | INC | 16.84% | -11.6 pts | -27.9% | Opponent Stronghold: Retained by INC in both elections. Strategic long-term penetration zone. | 1. Identify neutral voter clusters & youth groups. 2. Highlight Punjab state guarantees & civic development work. 3. Continuous outreach to chip away at INC base. |
| 37 | Gali Basant Singh Chowk Karedi, Nagar Nigam Amritsar Ward No. 46 + Gali Visakha Singh, Nagar Nigam Amritsar, Ward No. 46 + Gali Karam Singh, Nagar Nigam Amritsar, Ward No. 46 + Gali Mian Singh, Chowk Karedi to Gali Mona Singh, Nagar Nigam Amritsar, Ward No. 46 + Chowk Karedi Gali Mona Singh, Nagar Nigam Amritsar, Ward No. 46 + Gali Sarmukh Singh, Chowk Karedi Nagar Nigam Amritsar Ward No. 46 | AAP | 54.87% | AAP | 34.94% | -19.9 pts | -20.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.94% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.94% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 38 | Kucha Ramgarhian Chowk Baba Bohri Wala, Nagar Nigam Amritsar, Ward No. 46 + Gali Mai Mohno Baba Bohri Wala, Nagar Nigam Amritsar, Ward No. 46 + Main Bazar Chowk Baba Bohri Wala, Nagar Nigam Amritsar Ward No. 46 + Gali Masit Wali Chowk Baba Bohri Wala, Nagar Nigam Amritsar, Ward No. 46 + Gali Uttamgarh Main Bazar Chowk Baba Bohri Wala, Nagar Nigam Amritsar, Ward No. 46 + Akaliyan De Quarter, Nagar Nigam Amritsar Ward No. 46 + Jhaunti Nihang Singh Main Bazar Chowk Baba Bohri Wala, Nagar Nigam Amritsar Ward No. 46 + Gali Phat Wali Main Bazar Chowk Baba Bohri Wala, Nagar Nigam Amritsar, Ward No. 46 | AAP | 50.1% | AAP | 32.49% | -17.6 pts | -19.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (32.49% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 32.49% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 39 | Kishangarh, Nagar Nigam Amritsar Ward No. 46 + Gali Baba Deep Singh, Nagar Nigam Amritsar Ward No. 46 + Gali Variyam Singh Wali, Nagar Nigam Amritsar Ward No. 46 + Gali Ishar Singh, Nagar Nigam Amritsar, Ward No. 46 + Chowk Koreri, Nagar Nigam Amritsar Ward No. 46 + Chowk Manna Singh Main Road, Nagar Nigam Amritsar Ward No. 46 + Gali Dasodha Singh, Nagar Nigam Amritsar Ward No. 46 + Gali Budha Beant Singh, Nagar Nigam Amritsar Ward No. 46 + Gali Captain Piara Singh Shaheed, Nagar Nigam Amritsar Ward No. 46 + Gali Mehtab, Nagar Nigam Amritsar, Ward No. 46 + Gali Jawala Singh, Nagar Nigam Amritsar Ward No. 46 + Gali Koreri, Nagar Nigam Amritsar, Ward No. 46 + Gurdwara Ramsar Printing Press Quarter, Nagar Nigam Amritsar, Ward No. 46 + Gurdwara Bibeksar Road Quarters, Nagar Nigam Amritsar, Ward No. 46 + Guru Teg Bahadur Avenue, Nagar Nigam Amritsar, Ward No. 46 | AAP | 57.77% | AAP | 32.51% | -25.3 pts | -36.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (32.51% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 32.51% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 40 | Gali Lachhi Wali S-16, Nagar Nigam Amritsar, Ward No. 46 + Haveli Kohlu Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Darjian Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Heera Chopri Wali, Nagar Nigam Amritsar, Ward No. 46 + Chowk Kareri, Nagar Nigam Amritsar, Ward No. 46 + Gali Nihal Singh (Chowk Kareri), Nagar Nigam Amritsar, Ward No. 46 + Gali Atar Singh, Nagar Nigam Amritsar, Ward No. 46 + Gali Gopal Singh Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Lal Singh Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Mai Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Nihal Singh Khooh Wali, Nagar Nigam Amritsar, Ward No. 46 + Chowk Moni Haveli Rai Sahib, Nagar Nigam Amritsar, Ward No. 46 + Gali Varpalian, Nagar Nigam Amritsar, Ward No. 46 + Gali Sanpan Wali, Nagar Nigam Amritsar, Ward No. 46 + Chowk Moni Vehra, Nagar Nigam Amritsar, Ward No. 46 + Chowk Moni Atma Ram, Nagar Nigam Amritsar, Ward No. 46 + Gali Jassa Singh, Nagar Nigam Amritsar, Ward No. 46 + Chowk Moni, Nagar Nigam Amritsar, Ward No. 46 + Ramsar Road, Nagar Nigam Amritsar Ward No. 46 + Ramsar Road Chowk Kareri, Nagar Nigam Amritsar Ward No. 46 + Gali Jawahar Singh Chowk Kareri Nagar Nigam Amritsar Ward No. 46 + Bazar Chowk Kareri Moni, Nagar Nigam Amritsar Ward No. 46 | AAP | 46.54% | INC | 28.35% | -18.2 pts | -31.1% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-18.2 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 41 | Gali No. 1 Uttamgarh, Nagar Nigam Amritsar, Ward No. 46 + Gali No. 2 Uttamgarh Chowk Baba Bohri Wala, Nagar Nigam Amritsar, Ward No. 46 + Gali No. 3 Uttamgarh Chowk Baba Bohri Wala, Nagar Nigam Amritsar, Ward No. 46 + Uttamgarh Gali No. 3, Nagar Nigam Amritsar, Ward No. 46 + Gali No. 4 Bazar Baba Bohri Wala, Nagar Nigam Amritsar, Ward No. 46 + Bazar Baba Bohri Wala Bibeksar Road, Nagar Nigam Amritsar, Ward No. 46 + Baba Bohri Wala (Akhara), Nagar Nigam Amritsar, Ward No. 46 + Bibeksar Road Gali Berian Wali Puran Singh Marg, Nagar Nigam Amritsar, Ward No. 46 + Bibeksar Road, Nagar Nigam Amritsar, Ward No. 46 + Mahant Mall Singh Colony, Nagar Nigam Amritsar, Ward No. 46 | AAP | 57.95% | AAP | 37.43% | -20.5 pts | -23.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (37.43% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 37.43% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 42 | Gali Khanda Singh Wali Nagar Nigam Amritsar Ward No. 46 + Gali Punjab Singh Chowk Baba Sahib, Nagar Nigam Amritsar, Ward No. 46 + Koochan Singh Haveli Daroga, Nagar Nigam Amritsar, Ward No. 46 + Chowk Baba Sahib Main Bazar, Nagar Nigam Amritsar, Ward No. 46 + Gali Gianiian, Nagar Nigam Amritsar, Ward No. 46 + Gali Jai Singh, Nagar Nigam Amritsar, Ward No. 46 + Gali Pisoorian, Nagar Nigam Amritsar, Ward No. 46 + Dharamshala Doabian, Nagar Nigam Amritsar, Ward No. 46 + Gali Manmohat Singh, Nagar Nigam Amritsar, Ward No. 46 + Gali Narain Singh, Nagar Nigam Amritsar, Ward No. 46 + Chowk Parag Das Main Bazar, Nagar Nigam Amritsar, Ward No. 46 + Gali Nisanchian, Nagar Nigam Amritsar, Ward No. 46 | AAP | 52.14% | AAP | 54.18% | +2.0 pts | -25.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (54.18% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 54.18% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 43 | Gali Wadhau Wali, Nagar Nigam Amritsar, Ward No. 46 + Haveli Ganesh Das, Nagar Nigam Amritsar, Ward No. 46 + Gali Fatehbadia, Nagar Nigam Amritsar, Ward No. 46 + Chaur Gali (Shiv Gali), Nagar Nigam Amritsar, Ward No. 46 + Gali Shan Wali, Nagar Nigam Amritsar, Ward No. 46 + Chowk Baba Sahib, Nagar Nigam Amritsar, Ward No. 46 | AAP | 63.01% | BJP | 28.64% | -34.4 pts | -19.1% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-34.4 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 44 | Kot Harnamdas Gali No. 5, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnamdas Gali No. 6, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnamdas Gali No. 7, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 1, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 2, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 3, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 4, Nagar Nigam Amritsar, Ward No. 42 | AAP | 68.01% | AAP | 51.13% | -16.9 pts | -17.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (51.13% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 51.13% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 45 | Guru Nanak Pura Bazar No. 6, Nagar Nigam Amritsar, Ward No. 42 + Guru Nanak Pura Bazar No. 7 Barsati Wala Nala, Nagar Nigam Amritsar, Ward No. 42 + Krishna Nagar Near Purani Chungi Nagar Nigam Amritsar Ward No. 42 | AAP | 60.82% | AAP | 38.64% | -22.2 pts | -28.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (38.64% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 38.64% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 46 | Kot Harnam Das Gali No. 8, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 9, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 10, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 11, Nagar Nigam Amritsar, Ward No. 42 + Main Bazar Kot Harnam Das, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 12, Nagar Nigam Amritsar, Ward No. 42 + Kot Harnam Das Gali No. 13, Nagar Nigam Amritsar, Ward No. 42 | AAP | 49.11% | AAP | 40.38% | -8.7 pts | -24.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (40.38% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 40.38% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 47 | Kot Ralia Ram Sultanwind Road (Right Side), Nagar Nigam Amritsar, Ward No. 47 | AAP | 43.51% | INC | 32.42% | -11.1 pts | -34.1% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-11.1 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 48 | Kot Ralia Ram Sultanwind Road (Sajja Pasa), Nagar Nigam Amritsar, Ward No. 47 + Kot Baba Deep Singh Gali No. 1, Nagar Nigam Amritsar, Ward No. 47 + Abadi Mahant Lachhman Das, Nagar Nigam Amritsar, Ward No. 47 | AAP | 47.77% | AAP | 37.25% | -10.5 pts | -21.3% | AAP Retained: AAP led in both elections. High-priority bastion booth (37.25% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 37.25% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 49 | Rajhe di Haveli Guru Nanakpura Bazar, Nagar Nigam Amritsar, Ward No. 42 + Rajhe di Haveli, Nagar Nigam Amritsar, Ward No. 42 + Abai Guru Nanakpura Bazar No. 4, Nagar Nigam Amritsar, Ward No. 42 | AAP | 56.45% | AAP | 42.25% | -14.2 pts | -21.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.25% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.25% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 50 | Gurudwara Baba Jeevan Singh Guru Nanakpura Gali No. 7, Nagar Nigam Amritsar, Ward No. 47 + Gurudwara Baba Jeevan Singh Guru Nanakpura Gali No. 8, Nagar Nigam Amritsar, Ward No. 47 + Gurudwara Baba Jeevan Singh Guru Nanak Pura Gali No. 7, Nagar Nigam Amritsar, Ward No. 47 + Abadi Guru Nanak Pura Jujhari Abadi Sarwar Pura, Nagar Nigam Amritsar, Ward No. 47 + Abadi Guru Nanakpura Nede Ranjhe Di Haveli Gali No. 7, Nagar Nigam Amritsar, Ward No. 47 | AAP | 59.16% | AAP | 39.43% | -19.7 pts | -21.1% | AAP Retained: AAP led in both elections. High-priority bastion booth (39.43% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 39.43% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 51 | Antarjami Colony, Gali No. 6, Nagar Nigam Amritsar, Ward No. 42 + Antarjami Colony, Gali No. 2, Nagar Nigam Amritsar, Ward No. 42 + Antarjami Colony, Gali No. 4, Nagar Nigam Amritsar, Ward No. 42 + Antarjami Colony, Gali No. 5, Nagar Nigam Amritsar, Ward No. 42 + Antarjami Colony, Gali No. 7, Nagar Nigam Amritsar, Ward No. 42 + Antarjami Colony, Gali No. 8, Nagar Nigam Amritsar, Ward No. 42 + Antarjami Colony, Gali No. 9, Nagar Nigam Amritsar, Ward No. 42 + Antarjami Colony, Gali No. 3, Nagar Nigam Amritsar, Ward No. 42 | AAP | 63.59% | AAP | 38.01% | -25.6 pts | -26.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (38.01% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 38.01% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 52 | Antarjami Colony, Gali No. 1, Nagar Nigam Amritsar, Ward No. 42 + New Antarjami Colony, Gali No. 2, Nagar Nigam Amritsar, Ward No. 42 + New Antarjami Colony, Gali No. 1, Nagar Nigam Amritsar, Ward No. 42 + Main Bazar Antarjami Colony, Gali No. 1, Nagar Nigam Amritsar, Ward No. 42 + Baba Deep Singh Avenue Chatiwind Nala Taran Taran Road, Nagar Nigam Amritsar Ward No. 47 | AAP | 58.91% | AAP | 34.6% | -24.3 pts | -15.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.6% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.6% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 53 | Gali Masit Wali, Nagar Nigam, Amritsar, Ward No. 46 + Baba Deep Singh Colony, Nagar Nigam Amritsar, Ward No. 46 + Chowk Baba Deep Sahib, Nagar Nigam. Amritsar, Ward No. 46 | AAP | 55.61% | AAP | 32.5% | -23.1 pts | -13.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (32.5% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 32.5% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 54 | Abadi Fire Brigade, Nagar Nigam, Amritsar, Ward No. 48 + Gali Brahm Acharya Gill Wali Gate, Nagar Nigam Amritsar, Ward No. 48 + Gali Gor Kanda Guru Arjan Dev Gali, Nagar Nigam Amritsar, Ward No. 48 + Kucha Gujran Chowk Jai Singh, Nagar Nigam Amritsar, Ward No. 48 + Chowk Jai Singh, Nagar Nigam Amritsar, Ward No. 48 + Kucha Kahan Singh, Nagar Nigam Amritsar, Ward No. 48 | AAP | 66.93% | BJP | 30.51% | -36.4 pts | -19.6% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-36.4 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 55 | Chauk Lachhmansar, Nagar Nigam Amritsar, Ward No. 48 + Bakkar Wali Haveli, Nagar Nigam Amritsar, Ward No. 48 + Gali Bhaktiya, Nagar Nigam, Amritsar, Ward No. 48 + Gali Khajoor Wali, Nagar Nigam Amritsar, Ward No. 48 + Gali Khalsa Wali (Chauk Chabutra), Nagar Nigam, Amritsar, Ward No. 48 + Gali Leharaan, Nagar Nigam Amritsar, Ward No. 48 + Gali Kamboj, Nagar Nigam Amritsar, Ward No. 48 + Gali Saleta Wali, Nagar Nigam Ward No. 48 Amritsar | AAP | 60.03% | BJP | 31.62% | -28.4 pts | -19.0% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-28.4 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 56 | Chonk Chabutra, Nagar Nigam Amritsar, Ward No. 48 + Kucha Salamat Singh, Nagar Nigam Amritsar, Ward No. 48 + Gali Abdullah Khan, Nagar Nigam Amritsar, Ward No. 48 + Bazar Ambalwalian, Nagar Nigam Amritsar, Ward No. 48 | SAD | 19.96% | INC | 22.37% | +2.4 pts | -21.0% | Opponent Transition: Won by SAD in 2022 and shifted to INC in 2024. Volatile urban battleground. | 1. Analyze underlying voter dissatisfaction shifting between opponents. 2. Project AAP as stable local governance choice. 3. Mobilize pro-AAP ward committee. |
| 57 | Haveli Panna Singh, Nagar Nigam Amritsar, Ward No. 48 + Bazaar Chowk Moni, Nagar Nigam Amritsar, Ward No. 46 + Mandi Bhagat Singh Road, Nagar Nigam Amritsar, Ward No. 46 + Bazaar Androon Chatiwind, Nagar Nigam Amritsar, Ward No. 46 + Bazaar Loharan, Nagar Nigam Amritsar, Ward No. 48 + Gali Ali Munshi Gill Wali Gate, Nagar Nigam Amritsar, Ward No. 48 + Gali Mast Khooh, Nagar Nigam Amritsar, Ward No. 48 | AAP | 36.0% | INC | 13.74% | -22.3 pts | -22.8% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-22.3 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 58 | Ghar Maliyan De Sakatri Bagh, Nagar Nigam, Amritsar, Ward No. 50 + Lal Quarters Sakatri Bagh Bahar Var Anusuchit Jati Colony, Gilwali Gate, Nagar Nigam Amritsar, Ward No. 50, Amritsar + Baba Khadak Singh Baba Darshan Singh, I.T.I Vidyak Sanstha, Nagar Nigam Amritsar, Ward No. 47 + Gawala Enclave Kot Baba Deep Singh, Nagar Nigam Amritsar, Ward No. 47 + Tuttia Baba Sahaiya Singh Taran Taran Road, Nagar Nigam Amritsar, Ward No. 47 + Outside Gillwali Gate Main Road Nede, Nagar Nigam Amritsar, Ward No. 50 | AAP | 48.19% | BJP | 11.65% | -36.5 pts | -17.3% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-36.5 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 59 | Kachhe Pakke Ghar, Anusuchit Jati Colony, Dera Adhukiya Das, Nagar Nigam Amritsar, Ward No. 50, Amritsar. + Double Steri 24-Quarter, Nagar Nigam, Amritsar, Ward No. 50 + Shiv Bhola Nath Mandir, Nagar Nigam Amritsar, Ward No. 50 + Aare Wali, Nagar Nigam Amritsar, Ward No. 50 + Lakshmi Avenue Nede State Bank Bhagta Wala Road, Nagar Nigam Amritsar, Ward No. 50 + Pichhla Pasa Guru Ramdas Atta Mill Nagar Nigam Amritsar, Ward No. 50 + Tarsem Lal Dukanedar Ate Guru Ram Das Atta Mill, Nagar Nigam Amritsar, Ward No. 50 + Baba Jeevan Singh Colony, Railway Line Bhagta Wala Road, Nagar Nigam Amritsar, Ward No. 50 + Center Warehouse Railway Paar Nede Dana Mandi Bhagta Wala Road, Nagar Nigam Amritsar, Ward No. 50 | AAP | 35.35% | INC | 25.76% | -9.6 pts | -24.4% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-9.6 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 60 | Karkhana Bazar, Nagar Nigam Amritsar, Ward No. 46 + Purani Lakkad Mandi, Nagar Nigam Amritsar, Ward. 46 + Neevi Gali Nede Purani Lakkad Mandi, Nagar Nigam, Amritsar, Ward No. 46 + Valtoiyan Wali Gali, Mahana Singh Road, Nagar Nigam Amritsar, Ward No. 46 | AAP | 41.3% | BJP | 25.69% | -15.6 pts | -8.6% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-15.6 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 61 | Karkhana Bazar (Near Chauli Chowk), Nagar Nigam Amritsar, Ward No. 46 + Gali Phat Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Madan Lal Bhatia, Nagar Nigam Amritsar, Ward No. 46 + Basti Isaiyan, Nagar Nigam Amritsar, Ward No. 46 | AAP | 52.15% | AAP | 31.67% | -20.5 pts | -17.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (31.67% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 31.67% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 62 | Gali Mahna Singh, Nagar Nigam Amritsar, Ward No. 46 + Mahna Singh Road, Nagar Nigam Amritsar, Ward No. 46 + Bazar Bagh Jallian Wala, Nagar Nigam, Amritsar, Ward No. 46 + Haveli Mahanta Di (Nede Dholi Chowk), Nagar Nigam, Amritsar, Ward No. 46 + Haveli Mai Toni (Nede Dakkhana Dholi Chowk), Nagar Nigam Amritsar, Ward No. 46 + Singhariyan Wali Gali (Nede Dakkhana Dholi Chowk), Nagar Nigam Amritsar, Ward No. 46 + Haveli Babu Ram (Nede Dholi Chowk), Nagar Nigam Amritsar, Ward No. 46 + Gali Dasaunda Singh, Nagar Nigam Amritsar, Ward No. 46 | AAP | 57.11% | INC | 25.73% | -31.4 pts | -20.7% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-31.4 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 63 | Gali Chuhar Singh, Nagar Nigam Amritsar, Ward No. 46 + Chowk Manda Singh, Nagar Nigam Amritsar, Ward No. 46 + Gali Jiwan Choudhary, Nagar Nigam Amritsar, Ward No. 46 + Gali Amir Khushiar, Nagar Nigam Amritsar, Ward No. 46 + Chowk Manna Singh Gali Nadhalia Wali, Nagar Nigam Amritsar, Ward No. 46 + Gali Pippal Wali, Nagar Nigam Amritsar, Ward No. 46 + Mana Singh Road, Chowk Ghanta Ghar, Nagar Nigam Amritsar, Ward No. 46 | AAP | 54.65% | BJP | 23.06% | -31.6 pts | -17.5% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-31.6 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 64 | Gali Mangal Singh, Nagar Nigam Amritsar, Ward No. 46 + Akhara Chhat Wala, Nagar Nigam Amritsar, Ward No 46 + Sarai Guru Ramdas, Nagar Nigam Amritsar, Ward No. 46 + Budh Boota Market, Nagar Nigam Amritsar, Ward No. 46 + Madho Singh Road Gali No. 1, Nagar Nigam Amritsar, Ward No. 46 + Gali Sodhiyan, Nagar Nigam Amritsar, Ward No. 46 + Mahana Singh Road, Gali No 2, Nagar Nigam Amritsar, Ward No. 46 + Gali Thuthan Wali, Chowk Parag Das Nagar Nigam Amritsar Ward 46 + Akhara Budh Boota, Nagar Nigam Amritsar, Ward No. 46 + Dhobi Bazar, Nagar Nigam Amritsar, Ward No. 46 + Gali Samadhiyan, Nagar Nigam Amritsar, Ward No. 46 + Bazar Sarai, Guru Ramdas, Nagar Nigam Amritsar, Ward No. 46 + Gali Pujariyan Nede Bijli Ghar, Nagar Nigam Ward No. 46 Amritsar | AAP | 63.79% | AAP | 39.88% | -23.9 pts | -21.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (39.88% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 39.88% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 65 | Gali Thaiyan Nagar Nigam Amritsar, Ward No. 46 + Chowk Lachhmansar to Chowk Baba Sahib (Bagichi Seth Tara Chand), Nagar Nigam Amritsar, Ward No. 46 + Chowk Lachhmansar to Chowk Baba Sahib, Nagar Nigam Amritsar, Ward No. 46 + Gali Dabariya Wali, Nagar Nigam Amritsar, Ward No. 46 + Chowk Moni to Chowk Katri, Nagar Nigam Amritsar, Ward No. 46 | AAP | 59.17% | AAP | 44.9% | -14.3 pts | -20.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (44.9% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 44.9% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 66 | Kot Baba Deep Singh Gali No. 2, Nagar Nigam, Amritsar, Ward No. 47 + Kot Baba Deep Singh Gali No. 3, Nagar Nigam Amritsar, Ward No. 47 + Kot Baba Deep Singh Gali No. 4, Nagar Nigam Amritsar, Ward No. 47 | AAP | 63.68% | AAP | 33.89% | -29.8 pts | -21.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (33.89% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 33.89% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 67 | Kot Baba Deep Singh Gali No. 4, Nagar Nigam Amritsar, Ward No. 47 + Guru Ramdas Nagar Gali No. 1, Nagar Nigam Amritsar, Ward No. 47 + Kot Baba Deep Singh Gali No. 5, Nagar Nigam Amritsar, Ward No. 47 + Guru Ramdas Nagar Gali No. 3, Nagar Nigam Amritsar, Ward No. 47 | AAP | 60.2% | AAP | 48.05% | -12.2 pts | -20.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (48.05% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 48.05% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 68 | Guru Ramdas Nagar Gali No. 4, Nagar Nigam Amritsar, Ward No. 47 + Kot Baba Deep Singh Gali No 6 Nagar Nigam Amritsar, Ward No. 47 + Guru Ramdas Nagar Gali No. 2, Nagar Nigam. Amritsar, Ward No 47 | AAP | 40.44% | AAP | 40.25% | -0.2 pts | -23.1% | AAP Retained: AAP led in both elections. High-priority bastion booth (40.25% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 40.25% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 69 | Bahadur Nagar Sultan Pind Road (Right Side), Nagar Nigam Amritsar, Ward No. 47 + Kot Baba Deep Singh Gali No. 7, Nagar Nigam Amritsar, Ward No. 47 | AAP | 61.25% | AAP | 40.83% | -20.4 pts | -22.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (40.83% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 40.83% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 70 | Sardarpura Sultanwind Road, Nagar Nigam Amritsar, Ward No. 47 | AAP | 60.4% | AAP | 38.73% | -21.7 pts | -19.1% | AAP Retained: AAP led in both elections. High-priority bastion booth (38.73% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 38.73% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 71 | Nimbu Kot Aatma Ram, Nagar Nigam Amritsar, Ward No. 41 + Kot Aatma Ram, Nagar Nigam Amritsar, Ward No. 41 | AAP | 58.57% | AAP | 37.97% | -20.6 pts | -20.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (37.97% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 37.97% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 72 | Nimbu Kot Aatma Ram Gali No. 2, Nagar Nigam, Amritsar, Ward No. 41 | AAP | 54.41% | INC | 32.16% | -22.2 pts | -14.2% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-22.2 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 73 | New Shaheed Udham Singh Nagar gali.2, Nagar Nigam, Amritsar, Ward No. 43 + New Kapoor Nagar, Gali No.6, Nagar Nigam Amritsar.Ward No.40 | AAP | 58.98% | AAP | 46.3% | -12.7 pts | -27.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (46.3% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 46.3% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 74 | New Shaheed Udham Singh Nagar Gali.2, Nagar Nigam Amritsar, Ward No. 43 + New Kapur Nagar Gali No. 6, Nagar Nigam Amritsar, Ward No. 40 | AAP | 54.18% | AAP | 46.83% | -7.3 pts | -22.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (46.83% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 46.83% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 75 | New Kapoor Nagar Sultan Pind Road Gali No. 1,2,3,4,5, Nagar Nigam Amritsar, Ward No. 40 + New Kapoor Nagar Barf Karkhane Vali Gali, Nagar Nigam Amritsar, Ward No. 40 + New Kapoor Nagar Gali No. 6, Nagar Nigam Amritsar, Ward No. 40 | AAP | 60.0% | AAP | 52.18% | -7.8 pts | -37.3% | AAP Retained: AAP led in both elections. High-priority bastion booth (52.18% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 52.18% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 76 | Guru Nanak Nagar, Nagar Nigam Amritsar, Ward No. 42 + Kot Gurmeet Nagar, Nagar Nigam, Amritsar, Ward No. 41 + Kot Salig Ram, Nagar Nigam Amritsar, Ward No. 41 + Shaheed Udham Singh Nagar Gali No.4, Nagar Nigam, Amritsar, Ward No. 43 + New Shaheed Udham Singh Nagar Gali No.2, Nagar Nigam Amritsar, Ward No. 43 + Guru Nanak Nirankari Colony, Sultanwind Road, Nagar Nigam Ward No. 40 + New Shaheed Udham Singh Nagar Mehar Wala Bazar No.3, Nagar Nigam Ward 43 Amritsar | AAP | 52.06% | AAP | 38.08% | -14.0 pts | -29.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (38.08% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 38.08% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 77 | Shaheed Udham Singh Nagar Gali No.6, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Gali No.5, Nagar Nigam Amritsar, Ward No. 43 + New Shaheed Udham Singh Nagar Mandir Wala Bazar No.3, Nagar Nigam Ward No.43 Amritsar | AAP | 58.99% | AAP | 42.15% | -16.8 pts | -22.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.15% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.15% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 78 | Shaheed Udham Singh Nagar Gali No. 5, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Gali No. 3, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Gali No. 6, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Gali No. 4, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Bazar No. 5, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Mandir Wala Bazar Gali No. 8, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar No. 7, Nagar Nigam Amritsar, Ward No. 43 | AAP | 56.18% | AAP | 38.08% | -18.1 pts | -15.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (38.08% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 38.08% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 79 | New Shaheed Udham Singh Nagar Mandir Wala Bazar Gali No. 8, Nagar Nigam Amritsar, Ward No. 43 + New Shaheed Udham Singh Nagar Gali No. 3, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Bazar No. 5, Nagar Nigam Amritsar, Ward No. 43 | AAP | 53.72% | AAP | 42.09% | -11.6 pts | -37.0% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.09% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.09% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 80 | Jawala Ji Nagar Gali No. 8, Nagar Nigam Amritsar, Ward No. 42 + Kot Karnail Singh, Nagar Nigam Amritsar, Ward No. 42 + Jawala Ji Nagar Gali No. 7, Nagar Nigam Amritsar, Ward No. 42 | AAP | 53.58% | AAP | 37.06% | -16.5 pts | -32.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (37.06% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 37.06% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 81 | Bazar No. 3 Tej Nagar, Nagar Nigam, Amritsar Ward No. 42 + Bazar No. 2 Tej Nagar Sultanwind Road, Nagar Nigam Amritsar Ward No. 42 + New Tej Nagar, Nagar Nigam, Amritsar Ward No. 42 + Main Bazar Tej Nagar, Nagar Nigam Amritsar Ward No. 42 + Bazar No. 1 Tej Nagar Sultanwind Road, Nagar Nigam Amritsar Ward No. 42 | AAP | 48.85% | AAP | 39.43% | -9.4 pts | -26.9% | AAP Retained: AAP led in both elections. High-priority bastion booth (39.43% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 39.43% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 82 | New Shaheed Udham Singh Nagar Street No. 4, Municipal Corporation Amritsar, Ward No. 43 | AAP | 49.19% | AAP | 39.55% | -9.6 pts | -27.3% | AAP Retained: AAP led in both elections. High-priority bastion booth (39.55% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 39.55% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 83 | New Shaheed Udham Singh Gali No. 3, Nagar Nigam Amritsar, Ward No. 43 + New Shaheed Udham Singh Gali No. 2 Nagar Nigam Amritsar, Ward No. 43 | AAP | 64.33% | AAP | 49.54% | -14.8 pts | -28.9% | AAP Retained: AAP led in both elections. High-priority bastion booth (49.54% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 49.54% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 84 | Habib Pura Gali No. 2, 3, 4, 9 Nagar Nigam Amritsar, Ward No. 47 + Kot Harnam Das, Nagar Nigam Amritsar, Ward No. 42 + Habib Pura Sultan Wind Road, Nagar Nigam Amritsar, Ward No. 47 | AAP | 65.86% | AAP | 47.33% | -18.5 pts | -18.0% | AAP Retained: AAP led in both elections. High-priority bastion booth (47.33% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 47.33% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 85 | Habib Pura, Nagar Nigam Amritsar, Ward No 47 + Kot Harnam Das Bhag No.2, Nagar Nigam, Amritsar, Ward No. 42 + Teerth Pura Main Bazar, Nagar Nigam Amritsar, Ward No.47 + Ram Singh Gali No. 2, Nagar Nigam Amritsar, Ward No.47 + Sant Chandan Singh Colony, Nagar Nigam Amritsar, Ward No. 42 + Ram Singh Colony, Gali No. 1, Nagar Nigam Amritsar, Ward No. 42 + Bagihee Mahanta, Nagar Nigam Amritsar, Ward No.47 | AAP | 60.69% | AAP | 45.0% | -15.7 pts | -19.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (45.0% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 45.0% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 86 | Kot Aatma Ram Sultanwind Road, Nagar Nigam Amritsar, Ward No. 41 | AAP | 60.96% | AAP | 42.79% | -18.2 pts | -21.8% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.79% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.79% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 87 | Amiyadarjit Purana Dhobi Ghat, Nagar Nigam Amritsar, Ward No. 41 + Kot Atma Ram, Nagar Nigam, Amritsar, Ward No. 41 + Kot Salig Ram, Nagar Nigam, Amritsar, Ward No. 41 | AAP | 63.27% | AAP | 40.57% | -22.7 pts | -22.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (40.57% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 40.57% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 88 | Bhagat Singh Pura, Nagar Nigam Amritsar, Ward No. 41 + Dasmesh Colony, Nagar Nigam Amritsar, Ward No. 41 + Juhri Sultanwind Road, Nagar Nigam Amritsar, Ward No. 41 | AAP | 58.6% | AAP | 41.55% | -17.1 pts | -26.9% | AAP Retained: AAP led in both elections. High-priority bastion booth (41.55% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 41.55% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 89 | Shaheed Udham Singh Gali No.1, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Gali No. 5, Nagar Nigam Amritsar, Ward No. 43 | AAP | 62.37% | AAP | 41.03% | -21.3 pts | -29.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (41.03% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 41.03% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 90 | Shaheed Udham Singh Nagar Gali No.3, Nagar Nigam Amritsar, Ward No. 43 | AAP | 58.9% | AAP | 43.5% | -15.4 pts | -32.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (43.5% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 43.5% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 91 | Gaali No.6 Shaheed Udham Singh Nagar, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Gaali No.2, Nagar Nigam Amritsar, Ward No 43 | AAP | 51.47% | AAP | 37.44% | -14.0 pts | -36.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (37.44% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 37.44% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 92 | New Shaheed Udham Singh Nagar Gali No. 6, Nagar Nigam Amritsar, Ward No. 43 + New Shaheed Udham Singh Nagar Gali No. 4, Nagar Nigam Amritsar, Ward No. 43 + New Shaheed Udham Singh Nagar Mandir Wala Bazar Gali No. 10, Nagar Nigam Amritsar, Ward No. 43 + New Shaheed Udham Singh Nagar Gali No. 3, Nagar Nigam Amritsar, Ward No. 43 | AAP | 54.45% | AAP | 35.45% | -19.0 pts | -31.3% | AAP Retained: AAP led in both elections. High-priority bastion booth (35.45% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 35.45% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 93 | New Shaheed Udham Singh Nagar Bazar No. 5, Municipal Corporation Amritsar, Ward No. 43 + New Shaheed Udham Singh Nagar Gali No. 3, Municipal Corporation Amritsar, Ward No. 43 | AAP | 52.9% | AAP | 41.91% | -11.0 pts | -22.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (41.91% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 41.91% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 94 | New Shaheed Udham Singh Nagar Mandir Wala Bazar No.9, Nagar Nigam Amritsar, Ward No. 43 + New Shaheed Udham Singh Nagar Gali No. 3, Nagar Nigam Amritsar, Ward No. 43 + Shaheed Udham Singh Nagar Gali No. 6, Nagar Nigam Amritsar, Ward No. 43 | AAP | 46.27% | AAP | 47.74% | +1.5 pts | -34.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (47.74% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 47.74% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 95 | Jaspal Nagar Sultanwind Road, Nagar Nigam Amritsar, Ward No. 41 | AAP | 60.65% | AAP | 40.75% | -19.9 pts | -16.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (40.75% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 40.75% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 96 | New Jaspal Nagar Sultanwind Road, Nagar Nigam Amritsar, Ward No. 41 | AAP | 42.77% | AAP | 41.82% | -0.9 pts | -28.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (41.82% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 41.82% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 97 | Namdev Colony, Main Bazar, Nagar Nigam Amritsar, Ward No. 41 + Gali No.4 Namdev Colony, Near Gurudwara Toot Sahib, Nagar Nigam Amritsar, Ward No. 41 + Namdev Colony, Gali No.6 Gurudwara Toot Sahib, Nagar Nigam Amritsar, Ward No. 41 + Gali No 4 Namdev Colony, Gurdwara Toot Sahib, Nagar Nigam Amritsar, Ward No. 41 + Gali No. 6 Namdev Colony, Nagar Nigam Amritsar, Ward No. 41 + Jaspal Nagar Sultanwind Road, Nagar Nigam Amritsar, Ward No. 41 | AAP | 47.7% | AAP | 45.67% | -2.0 pts | -33.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (45.67% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 45.67% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 98 | New Jaspal Nagar Sultanwind Road, Nagar Nigam Amritsar, Ward No. 41 + Gali No. 4 Namdev Colony, Nagar Nigam Amritsar, Ward No. 41 | AAP | 49.51% | AAP | 44.44% | -5.1 pts | -32.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (44.44% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 44.44% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 99 | Akali Colony, Gurnam Nagar near Saint Kabir School, Municipal Corporation Amritsar, Ward No. 40 + New Gurnam Nagar Street No.20 Ward No. 40 | AAP | 49.0% | AAP | 42.93% | -6.1 pts | -22.8% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.93% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.93% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 100 | Booth 100 - Amritsar South | AAP | 56.72% | AAP | 50.82% | -5.9 pts | -25.9% | AAP Retained: AAP led in both elections. High-priority bastion booth (50.82% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 50.82% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 101 | Booth 101 - Amritsar South | AAP | 57.92% | AAP | 43.32% | -14.6 pts | -15.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (43.32% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 43.32% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 102 | Booth 102 - Amritsar South | AAP | 54.86% | AAP | 44.59% | -10.3 pts | -22.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (44.59% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 44.59% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 103 | Booth 103 - Amritsar South | AAP | 54.47% | AAP | 34.86% | -19.6 pts | -15.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.86% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.86% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 104 | Booth 104 - Amritsar South | AAP | 57.11% | AAP | 44.51% | -12.6 pts | -21.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (44.51% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 44.51% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 105 | Booth 105 - Amritsar South | AAP | 55.73% | AAP | 34.13% | -21.6 pts | -22.8% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.13% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.13% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 106 | Booth 106 - Amritsar South | AAP | 56.96% | AAP | 37.5% | -19.5 pts | -17.9% | AAP Retained: AAP led in both elections. High-priority bastion booth (37.5% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 37.5% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 107 | Booth 107 - Amritsar South | AAP | 51.71% | AAP | 31.08% | -20.6 pts | -18.1% | AAP Retained: AAP led in both elections. High-priority bastion booth (31.08% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 31.08% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 108 | Booth 108 - Amritsar South | AAP | 53.75% | INC | 27.94% | -25.8 pts | -23.0% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-25.8 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 109 | Booth 109 - Amritsar South | AAP | 39.86% | INC | 20.7% | -19.2 pts | -16.8% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-19.2 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 110 | Booth 110 - Amritsar South | AAP | 55.67% | AAP | 34.49% | -21.2 pts | -24.3% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.49% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.49% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 111 | Booth 111 - Amritsar South | AAP | 56.88% | AAP | 39.14% | -17.7 pts | -36.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (39.14% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 39.14% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 112 | Booth 112 - Amritsar South | AAP | 61.04% | AAP | 42.21% | -18.8 pts | -27.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.21% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.21% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 113 | Booth 113 - Amritsar South | AAP | 52.07% | AAP | 43.55% | -8.5 pts | -20.3% | AAP Retained: AAP led in both elections. High-priority bastion booth (43.55% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 43.55% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 114 | Booth 114 - Amritsar South | AAP | 58.5% | AAP | 34.31% | -24.2 pts | -27.8% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.31% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.31% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 115 | Booth 115 - Amritsar South | AAP | 58.11% | AAP | 41.1% | -17.0 pts | -26.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (41.1% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 41.1% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 116 | Booth 116 - Amritsar South | INC | 25.1% | INC | 32.52% | +7.4 pts | -11.7% | Opponent Stronghold: Retained by INC in both elections. Strategic long-term penetration zone. | 1. Identify neutral voter clusters & youth groups. 2. Highlight Punjab state guarantees & civic development work. 3. Continuous outreach to chip away at INC base. |
| 117 | Booth 117 - Amritsar South | SAD | 28.31% | AAP | 41.13% | +12.8 pts | -19.3% | Flipped to AAP: Won in 2024 after SAD led in 2022. High-momentum gain (+12.8 pts). Consolidate grassroots network. | 1. Round-1 field visit to celebrate gain (+12.8 pts). 2. Identify key community influencers who shifted from SAD. 3. Address unresolved local civic issues. 4. Institutionalize booth committee. |
| 118 | Booth 118 - Amritsar South | INC | 26.04% | AAP | 30.45% | +4.4 pts | -10.8% | Flipped to AAP: Won in 2024 after INC led in 2022. High-momentum gain (+4.4 pts). Consolidate grassroots network. | 1. Round-1 field visit to celebrate gain (+4.4 pts). 2. Identify key community influencers who shifted from INC. 3. Address unresolved local civic issues. 4. Institutionalize booth committee. |
| 119 | Booth 119 - Amritsar South | INC | 24.13% | INC | 26.68% | +2.5 pts | -14.1% | Opponent Stronghold: Retained by INC in both elections. Strategic long-term penetration zone. | 1. Identify neutral voter clusters & youth groups. 2. Highlight Punjab state guarantees & civic development work. 3. Continuous outreach to chip away at INC base. |
| 120 | Booth 120 - Amritsar South | AAP | 47.72% | AAP | 43.29% | -4.4 pts | -16.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (43.29% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 43.29% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 121 | Booth 121 - Amritsar South | AAP | 46.07% | AAP | 48.65% | +2.6 pts | +21.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (48.65% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 48.65% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 122 | Booth 122 - Amritsar South | AAP | 46.84% | AAP | 42.98% | -3.9 pts | +328.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.98% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.98% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 123 | Booth 123 - Amritsar South | AAP | 48.85% | AAP | 48.34% | -0.5 pts | -16.0% | AAP Retained: AAP led in both elections. High-priority bastion booth (48.34% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 48.34% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 124 | Booth 124 - Amritsar South | AAP | 49.09% | INC | 24.85% | -24.2 pts | +145.8% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-24.2 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 125 | Booth 125 - Amritsar South | AAP | 61.11% | AAP | 49.49% | -11.6 pts | -8.7% | AAP Retained: AAP led in both elections. High-priority bastion booth (49.49% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 49.49% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 126 | Daburji G.T. Road Right Side Chungi Sahib, Municipal Corporation Amritsar, Ward No. 36 | AAP | 35.89% | INC | 26.03% | -9.9 pts | -5.6% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-9.9 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 127 | Gali No 1, Nahre Paar, Daburji Road, Nagar Nigam, Amritsar, Ward No 36 + Alpha International City, G.T. Road, Daburji, Nagar Nigam Amritsar Ward No 36, Amritsar + Abadi Kanwar Farm Near OTC Corporate Foyer Field, Nagar Nigam Amritsar, Ward No. 36 + Kanwar Avenue, Nagar Nigam Amritsar Ward No 36, Amritsar | AAP | 40.4% | INC | 28.07% | -12.3 pts | -16.0% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-12.3 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 128 | Pyramid City, Municipal Corporation Amritsar, Ward No. 25 + Baba Budha Ji Avenue Municipal Corporation Amritsar, Ward No. 36 + Surya Vihar, Municipal Corporation Ward No. 36 Amritsar + Nimbu Baba Budha Ji Avenue, Municipal Corporation Ward No. 36 Amritsar | INC | 30.21% | INC | 32.14% | +1.9 pts | -22.0% | Opponent Stronghold: Retained by INC in both elections. Strategic long-term penetration zone. | 1. Identify neutral voter clusters & youth groups. 2. Highlight Punjab state guarantees & civic development work. 3. Continuous outreach to chip away at INC base. |
| 129 | Abadi Mandir Wale Plot, Subhash Colony, Gali No. 4, Nagar Nigam Amritsar, Ward No. 39 + Abadi Darshan Avenue, Nagar Nigam, Amritsar Ward No. 36, Amritsar + Darshan Avenue, B-Block, Sultanwind Road, Nagar Nigam, Amritsar, Ward No. 36, Amritsar + Abadi Bazigar G.T. Road, Nagar Nigam Amritsar, Ward No. 36 | AAP | 45.82% | AAP | 48.71% | +2.9 pts | -22.1% | AAP Retained: AAP led in both elections. High-priority bastion booth (48.71% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 48.71% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 130 | Sultanwind Abadi Lakha Singh, Municipal Corporation Amritsar, Ward No. 36 + Abadi Subhash Colony, Street No. 1, Municipal Corporation Amritsar, Ward No. 38 + Jasbir Nagar Daburji Road, Municipal Corporation Amritsar, Ward No. 36 + Abadi G.T. Road Field Amritsar, Municipal Corporation Amritsar, Ward No. 25 + New Darshan Avenue Municipal Corporation Ward No. 36 Amritsar | AAP | 40.14% | AAP | 36.33% | -3.8 pts | -45.8% | AAP Retained: AAP led in both elections. High-priority bastion booth (36.33% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 36.33% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 131 | Abadi Subhash Colony, Mandir Wali Side, Nagar Nigam Amritsar, Ward No. 39 + Gate Enclave, Near Taran Wala Pull, Nagar Nigam Amritsar, Ward No. 39 + Ujagar Nagar, Sultanwind Road Nagar Nigam, Amritsar, Ward No. 39 + Harkrishan Avenue, Nagar Nigam Amritsar, Ward No. 39 + Abadi Dasmesh Engineering Works, Nagar Nigam Amritsar, Ward No. 25 | AAP | 53.07% | AAP | 47.35% | -5.7 pts | +239.0% | AAP Retained: AAP led in both elections. High-priority bastion booth (47.35% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 47.35% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 132 | Mandar Colony, G.T. Road Side, Municipal Corporation Amritsar, Ward No. 39 + Ram Avenue, Municipal Corporation Amritsar, Ward No. 39 + Abadi Mandir Wale Plat, Subhash Colony, Street No. 4, Municipal Corporation Amritsar, Ward No. 39 | AAP | 49.67% | AAP | 48.31% | -1.4 pts | -21.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (48.31% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 48.31% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 133 | Abadi Kot Mit Singh, Nagar Nigam Amritsar, Ward No. 38 | AAP | 52.68% | AAP | 47.67% | -5.0 pts | -22.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (47.67% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 47.67% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 134 | Abadi Kot Mit Singh, Nagar Nigam Amritsar, Ward No. 38 | AAP | 45.91% | AAP | 48.53% | +2.6 pts | -20.0% | AAP Retained: AAP led in both elections. High-priority bastion booth (48.53% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 48.53% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 135 | Abadi Davinder Nagar, Nagar Nigam Amritsar, Ward No. 38 + Kot Vadhava Singh, Near Kecher Rice Mill, Nagar Nigam Amritsar, Ward No. 38 + Abadi Mata Ganga Ji Nagar, Nagar Nigam Amritsar, Ward No. 38 + Abadi Bagichi Bhagta Kot Mitt Singh, Nagar Nigam Amritsar, Ward No. 37 + Punjabi Bagh Colony, Nagar Nigam Ward No. 37 Amritsar | AAP | 47.11% | AAP | 38.78% | -8.3 pts | -29.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (38.78% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 38.78% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 136 | Sultanwind, Abadi Kot Mint Singh, Nagar Nigam Amritsar, Ward No. 38 + Abadi Kot Mint Singh Nagar Nigam Ward No. 38 | AAP | 40.7% | AAP | 40.52% | -0.2 pts | -26.1% | AAP Retained: AAP led in both elections. High-priority bastion booth (40.52% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 40.52% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 137 | Abadi Kot Mitt Singh, Nagar Nigam Amritsar, Ward No. 38 | AAP | 43.33% | AAP | 44.92% | +1.6 pts | -14.3% | AAP Retained: AAP led in both elections. High-priority bastion booth (44.92% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 44.92% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 138 | Abadi Gurduare Wali Gali Khalsa Nagar, Nagar Nigam Amritsar, Ward No. 38 + Abadi Gurduare To Agge Wali Gali Khalsa Nagar, Nagar Nigam Amritsar, Ward No. 38 + Abadi Kot Mitt Singh, Nagar Nigam Amritsar, Ward No. 38 + Kot Mitt Singh, Gali No. 1,2,3,4,5, Nagar Nigam Amritsar, Ward No. 38 | AAP | 56.42% | AAP | 42.12% | -14.3 pts | -25.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.12% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.12% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 139 | Sultanwind, Abadi Khalsa Nagar, Nagar Nigam Amritsar, O.G. 85 Ward No. 38 | AAP | 57.39% | AAP | 43.08% | -14.3 pts | -23.3% | AAP Retained: AAP led in both elections. High-priority bastion booth (43.08% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 43.08% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 140 | Abadi Khalsa Colony, Kot Mint Singh, Nagar Nigam Amritsar Ward No 38 + Abadi Gurduware Wali Gali Khalsa Nagar, Nagar Nigam Amritsar, Ward No. 38 | AAP | 47.33% | AAP | 44.13% | -3.2 pts | -46.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (44.13% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 44.13% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 141 | Abadi Main Bazar, Bhai Manjh Road, Mata Ganga Ji Nagar, Nagar Nigam, Amritsar Ward No. 38, Amritsar. + Abadi Mata Ganga Ji Nagar, Nagar Nigam Amritsar, Ward No. 38 | AAP | 41.36% | AAP | 54.67% | +13.3 pts | -25.6% | AAP Retained: AAP led in both elections. High-priority bastion booth (54.67% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 54.67% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 142 | Bhai Kanaiya Ji Birdh Ashram, Nagar Nigam, Amritsar, Ward No. 38 + Abadi Main Bazaar, Bhai Manjh Road, Mata Ganga Ji Nagar, Nagar Nigam, Amritsar Ward No 38, Amritsar. + Abadi Guruduware te Agge Vali Gali Khalsa Nagar, Nagar Nigam Amritsar, Ward No. 38 | INC | 28.61% | AAP | 38.46% | +9.8 pts | +91.0% | Flipped to AAP: Won in 2024 after INC led in 2022. High-momentum gain (+9.8 pts). Consolidate grassroots network. | 1. Round-1 field visit to celebrate gain (+9.8 pts). 2. Identify key community influencers who shifted from INC. 3. Address unresolved local civic issues. 4. Institutionalize booth committee. |
| 143 | Abadi Behiniwal, Nagar Nigam Amritsar, Ward No. 37 | AAP | 45.87% | AAP | 46.12% | +0.2 pts | -17.9% | AAP Retained: AAP led in both elections. High-priority bastion booth (46.12% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 46.12% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 144 | Abadi Taraf Behnival, Nagar Nigam Amritsar, Ward No. 39 | AAP | 43.36% | AAP | 51.43% | +8.1 pts | -12.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (51.43% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 51.43% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 145 | Abadi Patti Sultan, Nagar Nigam Amritsar, Ward No. 37 + Abadi Khalsa Colony, Opposite Petrol Pump, Nagar Nigam Amritsar, Ward No. 38 | SAD | 23.83% | INC | 28.22% | +4.4 pts | -8.5% | Opponent Transition: Won by SAD in 2022 and shifted to INC in 2024. Volatile urban battleground. | 1. Analyze underlying voter dissatisfaction shifting between opponents. 2. Project AAP as stable local governance choice. 3. Mobilize pro-AAP ward committee. |
| 146 | Abadi Taraf Bahinival, Nagar Nigam Amritsar, Ward No. 39 + Gulmarg Avenue, Nagar Nigam Amritsar, Ward No 39, Amritsar. + Diamond Estate, Sultanwind Road, Nagar Nigam Ward No.39 Amritsar + Silver City, Sultanwind Road Ward No.39 Amritsar | INC | 25.28% | INC | 27.81% | +2.5 pts | -19.6% | Opponent Stronghold: Retained by INC in both elections. Strategic long-term penetration zone. | 1. Identify neutral voter clusters & youth groups. 2. Highlight Punjab state guarantees & civic development work. 3. Continuous outreach to chip away at INC base. |
| 147 | Sultanwind (Taraf Behniwal), Nagar Nigam Amritsar, Ward No. 39 + Abadi Behniwal, Nagar Nigam Amritsar, Ward No. 39 + Temple Avenue, Nagar Nigam Ward No.39 Amritsar | AAP | 59.38% | AAP | 39.62% | -19.8 pts | -21.9% | AAP Retained: AAP led in both elections. High-priority bastion booth (39.62% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 39.62% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 148 | Abadi Taraf Behniwal, Nagar Nigam Amritsar, Ward No. 39 | AAP | 59.32% | AAP | 41.18% | -18.1 pts | -10.8% | AAP Retained: AAP led in both elections. High-priority bastion booth (41.18% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 41.18% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 149 | Randa Singh Nagar Taran Taran Road, Nagar Nigam Amritsar, Ward No. 44 + Baba Deep Singh Nagar Taran Taran Road (Sarabjit Nagar), Nagar Nigam Amritsar, Ward No. 44 | AAP | 54.25% | AAP | 34.5% | -19.8 pts | -4.0% | AAP Retained: AAP led in both elections. High-priority bastion booth (34.5% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 34.5% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 150 | Baba Deep Singh Avenue, Taran Taran Road, Near Bharat Palace, Municipal Corporation Amritsar Ward No 44, Amritsar. + Utam Nagar, Taran Taran Road, Municipal Corporation. Amritsar. Ward No 44, Amritsar. + Bagichi Lakha Singh Taran Taran Road, Municipal Corporation Amritsar. Ward No 45, Amritsar. + Mata Kaulan Ji Nagar, Amritsar Ward No 44 | AAP | 56.1% | INC | 33.76% | -22.3 pts | -23.1% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-22.3 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 151 | Hari Singh Avenue, Opposite Dera Sant Baba Bhuri Wala, Municipal Corporation Amritsar, Ward No. 44 + Ganda Singh Colony, Tarn Taran Road, Municipal Corporation Amritsar, Ward No. 44 | AAP | 57.0% | AAP | 36.59% | -20.4 pts | -27.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (36.59% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 36.59% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 152 | Booth 152 - Amritsar South | AAP | 63.98% | INC | 35.01% | -29.0 pts | -12.8% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-29.0 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 153 | Guru Amardas Nagar, Taran Taran Road Nagar Nigam Amritsar, Ward No. 42 + Kot Maida Singh Bagihi Mathwali, Nagar Nigam Amritsar, Ward No. 45 + Gali Murbe Wali New Krishna Nagar Taran Taran Road, Nagar Nigam Amritsar, Ward No. 44 | AAP | 68.61% | AAP | 40.06% | -28.6 pts | -13.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (40.06% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 40.06% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 154 | Krishna Nagar Gali No. 1,2 Dera Kale Shah, Municipal Corporation Amritsar, Ward No. 42 + Krishna Nagar Gali Murabbe Vali, Tarn Taran Road, Municipal Corporation Amritsar, Ward No. 44 + Gali Bardana Tarn Taran Road, Municipal Corporation Amritsar, Ward No. 44 | AAP | 50.06% | AAP | 35.09% | -15.0 pts | -20.5% | AAP Retained: AAP led in both elections. High-priority bastion booth (35.09% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 35.09% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 155 | Kot Mahana Singh Taran Taran Road, Nagar Nigam Amritsar, Ward No. 45 + Akali Quarter Kot Mahana Singh Taran Taran Road, Nagar Nigam Amritsar, Ward No. 45 + Kot Mahana Singh, Nagar Nigam Amritsar, Ward No. 45 + Dilbag Nagar Gali No. 1 Dera, Nagar Nigam Amritsar, Ward No. 45 + Dilbag Nagar, Nagar Nigam Amritsar, Ward No. 45 + Guru Amar Das Nagar Gali No. 5 Taran Taran Road, Nagar Nigam Amritsar, Ward No. 42 + Murabbe Wali Gali (Navi Abadi) Taran Taran Road, Nagar Nigam Amritsar, Ward No. 44 | AAP | 62.86% | AAP | 47.7% | -15.2 pts | -22.1% | AAP Retained: AAP led in both elections. High-priority bastion booth (47.7% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 47.7% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 156 | Kot Manda Singh Taran Taran Road, Municipal Corporation Amritsar, Ward No. 45 + Krishna Nagar Taran Taran Road Gali No. 3 Municipal Corporation Amritsar, Ward No. 45 + Gurdev Nagar, Municipal Corporation Amritsar, Ward No. 45 | AAP | 56.04% | AAP | 42.62% | -13.4 pts | -16.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.62% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.62% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 157 | Murabbe Wali Gali, Nagar Nigam Amritsar, Ward No. 45 | AAP | 58.07% | AAP | 42.35% | -15.7 pts | -35.9% | AAP Retained: AAP led in both elections. High-priority bastion booth (42.35% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 42.35% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 158 | Krishna Nagar Taran Taran Road Street No. 4, Municipal Corporation Amritsar, Ward No. 42 + Krishna Nagar Taran Taran Road Street No. 5, Municipal Corporation Amritsar, Ward No. 44 + Krishna Nagar Taran Taran Road Street No. 6, Municipal Corporation Amritsar, Ward No. 44 + Muhabbe Wali Gali, Municipal Corporation Amritsar, Ward No. 45 | AAP | 54.29% | AAP | 37.77% | -16.5 pts | -23.1% | AAP Retained: AAP led in both elections. High-priority bastion booth (37.77% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 37.77% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 159 | Dasmesh Nagar Gali No. 3, Nagar Nigam Amritsar, Ward No. 44 + Dasmesh Nagar Gali No. 2, Nagar Nigam Amritsar, Ward No. 44 + Ishwar Nagar, Gali No. 3, Nagar Nigam Amritsar, Ward No. 44 + Dasmesh Nagar Gali No. 1, Nagar Nigam Amritsar, Ward No. 50 + Atma Nagar, Gali No. 4, Nagar Nigam Amritsar, Ward No. 45 | AAP | 58.4% | AAP | 40.14% | -18.3 pts | -22.4% | AAP Retained: AAP led in both elections. High-priority bastion booth (40.14% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 40.14% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 160 | Guru Nanak Colony, Gali No. 1A Ward No. 44 + Dashmesh Nagar Gali No. 4, Nagar Nigam Amritsar, Ward No. 44 + Dashmesh Nagar Gali No. 5, Nagar Nigam Amritsar, Ward No. 45 + Guru Nanak Colony, Gali No. 6 Ward No. 45 + Baba Budha Ji Nagar, Nagar Nigam Amritsar, Ward No. 45 | AAP | 53.11% | BJP | 23.96% | -29.1 pts | -12.9% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-29.1 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 161 | New Shaheed Udham Singh Nagar Street No. 5, Municipal Corporation Amritsar, Ward No. 43 + Bagichi Lakha Singh Taran Taran Road Before Canal, Municipal Corporation Amritsar, Ward No. 45 + New Shaheed Udham Singh Nagar Street No. 2, Municipal Corporation Amritsar, Ward No. 43 + Dev Singh Sham Singh Rice Mill Bank Side Rajput Dharm Kanda Nagar Nigam Amritsar Ward No. 42 | AAP | 43.53% | INC | 25.67% | -17.9 pts | -25.0% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-17.9 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 162 | Shailer Wali Gali Sharma Colony, Nagar Nigam Amritsar, Ward No. 45 + Namak Wali Gali Sharma Colony, Nagar Nigam Amritsar, Ward No. 45 + New Guru Gobind Singh Nagar Gali No. 4, Nagar Nigam Amritsar, Ward No. 50 + New Guru Gobind Singh Nagar Gali No. 3, Nagar Nigam Amritsar, Ward No. 50 + Guru Nanak Colony, Gali No. 5 Ward No. 45 + Guru Nanak Colony, Gali No. 2, Nagar Nigam Amritsar, Ward No. 45 | AAP | 48.34% | BJP | 23.27% | -25.1 pts | -24.0% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-25.1 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 163 | Sharma Colony, Gali No. 1, Nagar Nigam Amritsar, Ward No. 45 + Main Bazar Guru Nanak Colony, Nagar Nigam Amritsar, Ward No. 45 + Chowk Chabutra, Nagar Nigam Amritsar, Ward No. 48 + Gali No. 1 Guru Gobind Singh Nagar, Nagar Nigam Amritsar, Ward No. 45 + Gali No. 1, Guru Gobind Singh Nagar, Nagar Nigam Amritsar, Ward No. 45 | AAP | 50.33% | AAP | 32.54% | -17.8 pts | -25.2% | AAP Retained: AAP led in both elections. High-priority bastion booth (32.54% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 32.54% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |
| 164 | Sharma Colony, Gali No. 2, Nagar Nigam Amritsar, Ward No. 45 + Sharma Colony, Gali No. 3, Nagar Nigam Amritsar, Ward No. 45 + Main Road Guru Gobind Singh Palace, Nagar Nigam Amritsar, Ward No. 45 + Guru Gobind Singh Nagar Gali No. 2, Nagar Nigam Amritsar, Ward No. 50 | AAP | 40.83% | INC | 16.44% | -24.4 pts | -26.6% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-24.4 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 165 | Guru Nanak Colony, Street No. 3, Nagar Nigam Amritsar, Ward No. 45 + Guru Nanak Colony, Main Bazaar, Nagar Nigam Amritsar, Ward No. 45 + Guru Nanak Colony, Street No. 7, Nagar Nigam Amritsar, Ward No. 45 | AAP | 47.22% | INC | 24.19% | -23.0 pts | -20.4% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-23.0 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 166 | Himmatpura Gali No. 2, Nagar Nigam Amritsar, Ward No. 50 + Himmatpura Gali No. 3, Nagar Nigam Amritsar, Ward No. 50 | INC | 25.36% | INC | 26.95% | +1.6 pts | -14.0% | Opponent Stronghold: Retained by INC in both elections. Strategic long-term penetration zone. | 1. Identify neutral voter clusters & youth groups. 2. Highlight Punjab state guarantees & civic development work. 3. Continuous outreach to chip away at INC base. |
| 167 | Guru Nanak Colony, Street No. 1A (Right Side), Nagar Nigam Amritsar, Ward No. 45 + Guru Gobind Singh Colony, Nagar Nigam Amritsar, Ward No. 50 + Chattha Rice Mills, Nagar Nigam Amritsar, Ward No. 45 | AAP | 36.76% | INC | 19.6% | -17.2 pts | -8.1% | Flipped away from AAP: Won by AAP in 2022, lost to INC in 2024 (-17.2 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to INC. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 168 | Gali No. 1, Nagar Nigam Colony, Nagar Nigam Amritsar, Ward No. 45 + Main Road Himmatpura, Nagar Nigam Amritsar, Ward No. 50 + Sher Singh Tarantaran Road, Nagar Nigam Amritsar, Ward No. 45 + Himmatpura, Gali No. 2, Nagar Nigam Amritsar, Ward No. 50 + Himmatpura Gali No. 1, Nagar Nigam Amritsar, Ward No. 50 | AAP | 42.45% | BJP | 24.57% | -17.9 pts | -22.1% | Flipped away from AAP: Won by AAP in 2022, lost to BJP in 2024 (-17.9 pts). Urgent counter-offensive required. | 1. Thorough audit of vote loss to BJP. 2. Immediate contact with disaffected urban voters & shopkeepers. 3. Resolve pending ward civic grievances. 4. Rebuild aggressive booth unit. |
| 169 | Gujarpura - 1 (Left Side), Nagar Nigam Amritsar, Ward No. 50 + Gujarpura - 2 (Right Side), Nagar Nigam Amritsar, Ward No. 50 + Gujarpura - 3 (Left Side), Nagar Nigam Amritsar, Ward No. 50 | AAP | 49.11% | AAP | 30.85% | -18.3 pts | -4.0% | AAP Retained: AAP led in both elections. High-priority bastion booth (30.85% vote share). Maintain active committee. | 1. Conduct Round-1 visit. 2. Defend 30.85% share against BJP/INC inroads. 3. Engage local mohalla elders & bazaar committees. 4. Verify voter additions. 5. Round-2 check-in. |